## Slide 1: Hemorrhagic Shock after elective spine surgery: Quality Improvement
Mariana Garcia
NURS 304
Heritage University Nursing Department
November 25, 2025
Dr. Khin Aungthein
Vana, P.K., Vottero, B.A., & Altmiller, G. (2023). Quality and safety education for nurses: Core competencies for nursing leadership and care management (3rd ed.). Springer Publishing Company.
Zakaluzny, S. (2024). Hemorrhagic Shock after Elective Spine Surgery: Failure to Rescue after Limited Response to Nursing Concerns. Hemorrhagic shock after elective spine surgery: Failure to rescue after limited response to nursing concerns. https://psnet.ahrq.gov/web-mm/hemorrhagic-shock-after-elective-spine-surgery-failure-rescue-after- limited-response-nursing

## Slide 2: Summary of Case Study
67-year-old male underwent ALIF spine surgery
Intraoperative bleeding difficult to control at bone graft site
In PACU: hypotension, diaphoresis, pallor, back/pelvic pain, “impending doom”
Nurse notified surgeon three times; concerns were not acknowledged
Only fluids were ordered (No blood transfusion or rapid response)
Result: Multiorgan failure from hypovolemic shock
Notes: In this case, a 67-year-old man had elective ALIF spine surgery. During surgery, bleeding at the bone graft site was difficult to control. After surgery in the PACU, the patient showed concerning symptoms — low blood pressure, pale and sweaty skin, severe back and pelvic pain, and even said he felt ‘not right.’ The PACU nurse called the surgeon three times, but the concerns were not acted on. Only fluids were ordered, and no rapid response or blood transfusion was initiated. Overnight, the patient continued to decline and eventually died from multiorgan failure due to untreated hemorrhagic shock.

## Slide 3: Takeaways for quality improvement (QI)
1. Early recognition of shock
- Watch for early signs
- Worsening symptoms require immediate escalation
- Acting early can prevent shock from worsening
2. Clear Nurse-Provider communication
- Nurses must feel confident speaking up when a patient declines
- Repeated concerns must lead to action, not dismissal
- Using tools like SBAR can improve quality and urgency
Notes: There are two major lessons from this case. First, early recognition of shock is critical. When symptoms worsen, escalation must happen immediately. Second, clear nurse-provider communication is essential. Nurses should feel confident speaking up, and concerns should never be ignored. Tools like SBAR can help communicate urgency and protect patients.

## Slide 4: Quality Improvement Project
Problem Statement:
A postoperative spine surgery patient showed early signs of hypovolemic shock, but these signs were not acted on.
The PACU nurse’s repeated concerns were ignored, delaying care.
The patient received only fluids instead of blood, and no rapid response was activated.
Who Is Affected:
The patient (risk of shock, organ failure, death)
PACU nurses (concerns dismissed, moral distress)
Surgeons and the hospital (safety event, liability, poor communication)
Why This Matters:
Delayed recognition of bleeding is dangerous and preventable.
Lack of escalation can lead to failure-to-rescue, causing severe harm or death.
Improving communication and early response can save lives and improve patient safety.
Notes: This led me to develop a quality improvement project focused on improving early recognition and escalation of postoperative bleeding in the PACU.

## Slide 5: Aims
SMART: Increase timely recognition and escalation of postoperative bleeding in the PACU by 30% within 3 months through use of SBAR
Process: Increase RN use of SBAR during calls to providers about concerning vital signs
Outcome: Decrease delays in provider response when abnormal vitals or symptoms are reported.
Notes: My SMART aim is to increase timely recognition and escalation of postoperative bleeding by 30% within 3 months by using SBAR. My process aim is to increase RN use of SBAR when calling providers about concerning vital signs. My outcome aim is to decrease delays in provider response when abnormal vitals or symptoms are reported.

## Slide 6: Measures
Outcome Measure
Provider response time
  Calls with provider response ≤ 15 min
  All RN calls for concerning vitals
Process Measure
RN use of SBAR
  RN to provider calls using SBAR
  Total RN to provider calls about abnormal findings
Balancing Measure
Unnecessary escalations
  Escalations not clinically needed
  All escalations made
Why these measures?
They directly address the case problem: delayed recognition + poor communication → failure-to-rescue.
Notes: To know whether improvement is happening, I will measure three things:
For the outcome measure, I’ll track provider response time. The numerator is the number of calls where the provider responded within 15 minutes, and the denominator is all RN calls about concerning vital signs.
For the process measure, I’ll track how often SBAR is actually used. The numerator is RN calls using SBAR, and the denominator is total RN calls about abnormal findings.
For the balancing measure, I’ll track unnecessary escalations to make sure we’re not over-calling providers.

## Slide 7: Changes
1. Use SBAR for All Escalation Calls (Standardizes communication & helps nurses clearly state the concern and what action is needed)
2. Use an Early Warning Sign Checklist
- Includes red flags for shock: low BP, clammy skin, weak pulse, worsening pain
- Guides nurses on when to escalate
3. Create a Simple Nurse Escalation Pathway (Ensures concerns are not ignored)
4. Provide Quick Staff Education (Teach signs of hemorrhagic shock & Teach when and how to use SBAR)
5. Use QI Tools to Support Change
- Root Cause Analysis (RCA): Understand why communication failed
- PDSA Cycle: Test and refine the new escalation process
Notes: To reach the aim, several changes will be made. First, require SBAR for all escalation calls. Second, use an early-warning checklist to identify signs of bleeding and shock. Third, create a simple escalation pathway so concerns can move from the RN to the charge nurse, provider, and rapid response if needed. Fourth, provide brief education on shock signs and when to escalate. And finally, use QI tools like Root Cause Analysis and a PDSA cycle to test and refine the process.

## Slide 8: Achievability
Changes are realistic: SBAR and early-warning checklists are simple tools nurses already know how to use
Resources available: Charge nurses, PACU staff, and leadership can support the new escalation pathway
Low cost: Only brief teaching and reminders are needed. No new equipment required
Clear timeline: Education + pilot testing can happen within 2–4 weeks, with improvement measured over 3 months
Supportive environment: Leadership wants to prevent failure-to-rescue.
Notes: These changes are realistic because SBAR and early-warning checklists are tools nurses already use. We have the resources — PACU nurses, charge nurses, and leadership. This project is low cost and requires only short training and reminders. Education and pilot testing can happen within 2–4 weeks, and improvement can be measured over 3 months. Leadership support makes this change achievable

## Slide 9: Testing and Monitoring
Plan–Do–Study–Act (PDSA) Cycle
Plan: Pilot SBAR + Escalation Pathway in the PACU for 2–4 weeks.
Do: Educate nurses, start using SBAR for all urgent calls, track escalations.
Study: Review provider response times, number of escalations, quality of SBAR documentation, and patient outcomes.
Act: Identify barriers, adjust the pathway, provide extra training, and expand the process to more surgical units
Notes: PDSA is good to use because it lets us try the intervention, evaluate it, adjust, and repeat until we get the best results
To test the change, I would use a PDSA cycle.
Plan: Pilot SBAR and the escalation pathway in the PACU. Do: Educate nurses and start documenting SBAR use. Study: Review response times, escalation frequency, and SBAR documentation. Act: Adjust the pathway or education based on feedback, and then expand it to other units if successful.

## Slide 10: Project summary
Project Outcomes:
Increased use of SBAR during RN–provider calls
Faster provider response to abnormal vital signs
Improved early recognition of postoperative bleeding
Goal Achievement:
SMART aim met if SBAR use increases by 30% and response times improve
Sustainability:
Can be sustained with ongoing SBAR reminders, quick refreshers, and leadership support
Early-warning checklist can remain part of routine PACU workflow
Spreadability:
Improvements can be shared with other surgical units
Escalation pathway and SBAR training can be used hospital-wide
Notes: Overall, this project aims to prevent failure-to-rescue by improving communication and early recognition. Expected outcomes include increased SBAR use, faster provider response, and earlier detection of postoperative bleeding. The goal will be achieved if SBAR use increases by 30% and response times improve. These improvements can be sustained through ongoing reminders, brief refreshers, and leadership support. The process can also be shared with other surgical units and eventually hospital-wide.

## Slide 11: Thank you!
Notes: 10–30% is a common starting goal, so I picked 30% to aim for meaningful but realistic improvement
Any change can face pushback at first, but with support and practice, it becomes normal.
It makes sure concerns don’t stop with one person — the issue keeps moving up until the patient gets help